# BECP — XP Release Plan

Blockchain-based Extracurricular Credentials Platform  ·  TP075129  ·  APU BSc Software Engineering

Project dates: March 2026 – June 2026  ·  Methodology: Extreme Programming (XP)  ·  Developer: Muhammad Qayyum bin Mahamad Yazid

## 1. Project Overview

BECP is a blockchain-based credential platform that issues soulbound NFT micro-credentials to university students upon completion of extracurricular activities. The system serves four user roles — students, event organizers, university administrators, and HR recruiters — and is built on Optimism L2 using an ERC-1155 soulbound token standard.

## 2. Release Summary

| Release | Phase(s) | Deliverable | Target |
| --- | --- | --- | --- |
| R1 | Phase 0 + 1 | Monorepo scaffold + ERC-1155 soulbound smart contract + full test suite + Hardhat 3 deployment config | Week 1–2 |
| R2 | Phase 2 | Next.js 16 frontend skeleton — wallet authentication (RainbowKit), role detection, routing structure for all 4 user types | Week 3–4 |
| R3 | Phase 3A–3B | Certificate issuance flow (organizer → student NFT mint) + student credential dashboard (wallet cert gallery + skill tags) | Week 5–6 |
| R4 | Phase 3C–3D | Gamified skill progression charts (Recharts) + events marketplace with AI skill inferencing | Week 7–8 |
| R5 | Phase 3E–3G | Recruiter verification portal (QR → on-chain proof) + exportable portfolio with QR codes + OP Mainnet production deployment | Week 9–10 |

## 3. XP Values Applied

| XP Value | How it manifests in BECP |
| --- | --- |
| Communication | Daily pairing between student and AI assistant; all decisions documented in artifacts. |
| Simplicity | Soulbound logic implemented via a single _update override; no unnecessary abstractions. |
| Feedback | 52 unit tests give immediate feedback on every contract change; test-first for all features. |
| Courage | Chose Hardhat 3 beta + Bun over stable tooling to align with industry direction. |
| Respect | Contract NatSpec documents every design decision for future maintainers and the examiner. |

# BECP — Iteration Plan: Release 1

Phase 0 (Monorepo Scaffold)  +  Phase 1 (Smart Contract)  ·  Week 1–2

## 1. Iteration Goals

- Establish a working pnpm monorepo with Turborepo task pipeline

- Implement and fully test the BECPCredential ERC-1155 soulbound contract

- Configure Hardhat 3 for local OP simulation, OP Sepolia testnet, and OP Mainnet

- 52 unit tests passing — all XP acceptance criteria verified

## 2. Phase 0 — Monorepo Scaffold

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Create pnpm workspace + Turborepo config (turbo.json, pnpm-workspace.yaml) | Qayyum | 1 | 1 | DONE |
| Scaffold apps/web — Next.js 16 + TypeScript + Tailwind + ShadCN | Qayyum | 1 | 1.5 | DONE |
| Scaffold contracts/ — Hardhat 3 + hardhat-toolbox-viem + OpenZeppelin v5 | Qayyum | 1 | 1 | DONE |
| Scaffold packages/shared — shared TypeScript types and platform constants | Qayyum | 1 | 1 | DONE |
| Configure tsconfig.base.json path aliases (@becp/shared, @/*) | Qayyum | 0.5 | 0.5 | DONE |
| Set up Wagmi v2 + RainbowKit v2 Web3Provider in apps/web | Qayyum | 1 | 1 | DONE |
| Define shared types: CredentialMetadata, UserRole, SkillTag, BECPEvent | Qayyum | 1 | 1 | DONE |
| Define platform constants: chain IDs, contract roles, IPFS helpers, routes | Qayyum | 0.5 | 0.5 | DONE |
| Write setup.sh first-time setup script + .env.local.example files | Qayyum | 0.5 | 0.5 | DONE |

Phase 0 Total — Estimated: 7.5 hrs  ·  Actual: 8 hrs

## 3. Phase 1 — Smart Contract

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Design IBECPCredential interface — all events, errors, structs, and function signatures | Qayyum | 1 | 1 | DONE |
| Implement CredentialLib — pure validation helpers (URI, address, recipients) | Qayyum | 0.5 | 0.5 | DONE |
| Implement BECPCredential — ERC-1155 + ERC1155Pausable + ERC1155Supply + AccessControl | Qayyum | 3 | 3.5 | DONE |
| Implement two-tier role model (DEFAULT_ADMIN → UNIVERSITY_ADMIN → ISSUER) | Qayyum | 0.5 | 0.5 | DONE |
| Implement soulbound logic via _update override (mint/burn only) | Qayyum | 0.5 | 0.5 | DONE |
| Implement registerCredentialType with IPFS URI validation | Qayyum | 0.5 | 0.5 | DONE |
| Implement issueCredential + batchIssueCredential with atomic validation | Qayyum | 1 | 1 | DONE |
| Implement revokeCredential with dual-authority (issuer or uni admin) | Qayyum | 0.5 | 0.5 | DONE |
| Implement pause/unpause emergency controls via ERC1155Pausable | Qayyum | 0.5 | 0.5 | DONE |
| Implement getStudentCredentials with two-pass live balance filter | Qayyum | 0.5 | 0.5 | DONE |
| Write deploy.ts Hardhat Ignition deployment script | Qayyum | 0.5 | 0.5 | DONE |
| Configure hardhat.config.ts for hardhatOp / opSepolia / opMainnet | Qayyum | 0.5 | 0.5 | DONE |
| Write BECPCredential.test.ts — 52 tests across 10 describe blocks (Node test runner + Viem) | Qayyum | 3 | 4 | DONE |
| Debug and fix: address checksum normalisation (getAddress in describe body) | Qayyum | 1 | 1.5 | DONE |
| Debug and fix: stale artifact causing EnforcedPause and ZeroAddress failures (hardhat clean) | Qayyum | 0.5 | 0.5 | DONE |
| Debug and fix: uri() using exists() instead of _validateCredentialType() | Qayyum | 0.5 | 0.5 | DONE |
| All 52 tests passing ✓ | Qayyum | — | — | DONE |

Phase 1 Total — Estimated: 13.5 hrs  ·  Actual: 15 hrs

Release 1 Total — Estimated: 21 hrs  ·  Actual: 23 hrs

## 4. Retrospective Notes

| Category | Note |
| --- | --- |
| Went well | Test-first approach caught the uri() bug before any frontend integration. Hardhat 3 Viem migration was cleaner than expected once the async describe / before() timing issue was understood. |
| Went well | Moving wallet setup into the async describe body (instead of before()) eliminated all address-related test failures in one change. |
| Went over | Hardhat 3 tooling differences (configVariable, chainType, edr-simulated) required additional research time not anticipated in the estimate. |
| Went over | Debugging the ERC1155Pausable / Pausable inheritance chain for whenNotPaused on non-_update functions added ~1 hr to Phase 1. |
| Action item | For Phase 2: establish Wagmi contract hooks pattern before building any UI components to avoid later refactoring. |

# BECP — User Stories: Release 1

Phase 0 + Phase 1  ·  All stories verified by passing test suite

## US-01 — University Admin

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-01 | University Admin | Must Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a university admin, I want to approve event organizers so that only verified parties can issue credentials."

Acceptance Criteria:

- ✓  Admin can grant UNIVERSITY_ADMIN_ROLE to staff wallets

- ✓  University admin can call approveOrganizer() to grant ISSUER_ROLE

- ✓  University admin can call revokeOrganizer() to remove ISSUER_ROLE

- ✓  OrganizerApproved and OrganizerRevoked events are emitted with correct args

- ✓  A plain organizer cannot approve other organizers

- ✓  Zero address is rejected with ZeroAddress error

Test coverage: Section 2 — Two-Tier Organizer Trust Model (5 tests)

## US-02 — Event Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-02 | Event Organizer | Must Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As an approved event organizer, I want to register a credential type for my event so that I can later issue it to participants."

Acceptance Criteria:

- ✓  Organizer can call registerCredentialType() with a valid ipfs:// URI

- ✓  Each registration returns a unique auto-incrementing token ID starting from 1

- ✓  CredentialTypeRegistered event is emitted with tokenId, issuer address, and URI

- ✓  Non-IPFS URIs and empty strings are rejected with EmptyString error

- ✓  Non-issuers cannot register credential types

- ✓  uri(tokenId) returns the correct IPFS URI immediately after registration (before any minting)

Test coverage: Section 3 — Credential Type Registration (8 tests)

## US-03 — Event Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-03 | Event Organizer | Must Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As an event organizer, I want to issue a credential to a student after they complete my event so that their achievement is recorded on-chain."

Acceptance Criteria:

- ✓  Organizer can call issueCredential(tokenId, recipient) for an active credential type

- ✓  Student balance becomes 1 after issuance

- ✓  hasCredential() returns true after issuance

- ✓  CredentialIssued event is emitted with correct tokenId, recipient, and issuer

- ✓  Issuing to zero address reverts with ZeroAddress

- ✓  Issuing a credential the student already holds reverts with AlreadyIssued

- ✓  Issuing a non-existent tokenId reverts with TokenIdNotFound

- ✓  Non-issuers cannot call issueCredential

Test coverage: Section 4 — Single Credential Issuance (8 tests)

## US-04 — Event Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-04 | Event Organizer | Must Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As an event organizer, I want to batch-issue credentials to all participants in one transaction so that post-event certificate drops are gas-efficient."

Acceptance Criteria:

- ✓  Organizer can call batchIssueCredential(tokenId, recipients[]) for a list of student wallets

- ✓  All recipients hold the credential after a successful batch

- ✓  CredentialIssued event is emitted once per recipient

- ✓  If any recipient already holds the credential, the entire batch reverts (atomicity)

- ✓  Empty recipients array reverts with ZeroAddress

- ✓  Any zero address in the array reverts with ZeroAddress before any minting occurs

Test coverage: Section 5 — Batch Credential Issuance (5 tests)

## US-05 — University Admin / Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-05 | University Admin / Organizer | Must Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a university admin or the original issuer, I want to revoke a credential from a student so that invalid or fraudulent credentials can be invalidated."

Acceptance Criteria:

- ✓  Original issuer can call revokeCredential(tokenId, recipient, reason)

- ✓  University admin can revoke any credential regardless of issuer

- ✓  Student balance becomes 0 after revocation

- ✓  hasCredential() returns false after revocation

- ✓  CredentialRevoked event is emitted with tokenId, recipient, revokedBy, and reason

- ✓  Revoked credentials are excluded from getStudentCredentials()

- ✓  Revoking a credential not held by the student reverts with NotIssued

- ✓  Empty reason string reverts with EmptyString

- ✓  Strangers cannot revoke credentials

Test coverage: Section 6 — Credential Revocation (8 tests)

## US-06 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-06 | Student | Must Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a student, I want my credentials to be non-transferable so that my portfolio cannot be sold or reassigned to another wallet."

Acceptance Criteria:

- ✓  safeTransferFrom always reverts with SoulboundToken regardless of caller

- ✓  safeBatchTransferFrom always reverts with SoulboundToken

- ✓  Transfer is blocked even when the student has granted approval to another wallet

- ✓  Minting (from == address(0)) and burning (to == address(0)) are unaffected

Test coverage: Section 7 — Soulbound Token Transfers (3 tests)

## US-07 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-07 | Student | Must Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a student, I want to query all credentials in my wallet so that my dashboard can display my complete credential portfolio."

Acceptance Criteria:

- ✓  getStudentCredentials(address) returns all token IDs for which the student has balance > 0

- ✓  Returns an empty array for a student with no credentials

- ✓  Revoked credentials are excluded from the returned array (live balance filter)

- ✓  Re-issuance after revocation correctly re-includes the credential

Test coverage: Section 8 — Student Credential Portfolio (3 tests)

## US-08 — Platform Admin

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-08 | Platform Admin | Should Have | R1 / Phase 1 | DONE |
| --- | --- | --- | --- | --- |

Story:

"As the platform admin, I want to pause all minting operations in an emergency so that I can respond to a compromised issuer key without redeploying."

Acceptance Criteria:

- ✓  Admin can call pause() to halt all minting and registration

- ✓  While paused, issueCredential reverts with EnforcedPause

- ✓  While paused, registerCredentialType reverts with EnforcedPause

- ✓  Admin can call unpause() to resume operations

- ✓  Non-admins cannot call pause()

Test coverage: Section 9 — Emergency Pause (4 tests)

# BECP — CRC Cards: Smart Contract Layer

Component Responsibility Collaborator cards for Phase 1 contract architecture

| BECPCredential · Main Contract |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Register new credential types with IPFS metadata URI - Issue soulbound ERC-1155 tokens to student wallets - Batch issue tokens to multiple students atomically - Revoke credentials and emit immutable audit log - Enforce soulbound constraint — block all token transfers - Manage role hierarchy via AccessControl - Expose student credential portfolio query - Support emergency pause/unpause by admin - Return per-token IPFS metadata URI via uri() | - IBECPCredential (implements interface) - ERC1155 (token ledger) - ERC1155Pausable (pause logic in _update) - ERC1155Supply (totalSupply tracking) - ERC1155Burnable (burn for revocation) - AccessControl (role management) - CredentialLib (input validation) |

| IBECPCredential · Interface |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Define stable public ABI surface for frontend Wagmi hooks - Declare all custom errors (SoulboundToken, AlreadyIssued, etc.) - Declare all events (CredentialIssued, CredentialRevoked, etc.) - Define CredentialType struct for on-chain storage - Document role model and token model in NatSpec | - BECPCredential (implementation) - Frontend ABI consumer (Wagmi v2) |

| CredentialLib · Library (Validation) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Validate metadata URI has ipfs:// prefix and non-zero CID - Validate addresses are non-zero - Validate recipient arrays are non-empty and contain no zero addresses | - BECPCredential (consumer) |

| ERC1155Pausable · OZ Extension |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Provide _pause() and _unpause() internal functions - Provide whenNotPaused modifier for minting/registration functions - Hook into _update to enforce pause on all token movements - Emit EnforcedPause custom error when paused operations are attempted | - BECPCredential (inherits) - Pausable (internally wraps) |

| ERC1155Supply · OZ Extension |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Track totalSupply per token ID - Provide exists(tokenId) — returns true when totalSupply > 0 - Hook into _update to maintain supply counts on mint/burn | - BECPCredential (inherits) |

| AccessControl · OZ Access Control |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Manage role assignments (grant, revoke, check) - Enforce onlyRole modifier on protected functions - Support role hierarchy: UNIVERSITY_ADMIN_ROLE admins ISSUER_ROLE | - BECPCredential (inherits) |