# BECP — XP Release Plan (Updated: Release 2)

Blockchain-based Extracurricular Credentials Platform  ·  TP075129  ·  APU BSc Software Engineering

Project dates: March 2026 – June 2026  ·  Methodology: Extreme Programming (XP)  ·  Developer: Muhammad Qayyum bin Mahamad Yazid

## 1. Project Overview

BECP is a blockchain-based credential platform issuing soulbound ERC-1155 NFT micro-credentials to university students upon completing extracurricular activities. The system serves four roles — students, organizers, university administrators, and HR recruiters — deployed on Optimism L2. Release 2 delivers the complete Next.js 16 frontend skeleton: wallet authentication, on-chain role detection, portal routing for all four user types, off-chain student profile management, and a fully functional on-chain credential verification page.

## 2. Release Summary

| Release | Phase(s) | Deliverable | Target | Status |
| --- | --- | --- | --- | --- |
| R1 | Phase 0 + 1 | Monorepo scaffold + ERC-1155 soulbound smart contract + 52 passing tests + Hardhat 3 deployment config | Week 1–2 | DONE |
| R2 | Phase 2 | Next.js 16 frontend skeleton — wallet auth (RainbowKit), on-chain role detection, routing for all 4 user types, off-chain student profile API, functional verify page, frontend test suite (58 tests) | Week 3–4 | DONE |
| R3 | Phase 3A–3B | Credential issuance flow (organizer → student NFT mint) + student credential dashboard (wallet cert gallery + skill tags) | Week 5–6 | PENDING |
| R4 | Phase 3C–3D | Gamified skill progression (Recharts) + events marketplace with AI skill inferencing | Week 7–8 | PENDING |
| R5 | Phase 3E–3G | Recruiter verification portal (QR → on-chain proof) + exportable portfolio + OP Mainnet production deployment | Week 9–10 | PENDING |

## 3. XP Values Applied in Release 2

| XP Value | How it manifests in Release 2 |
| --- | --- |
| Communication | Architecture decisions (route groups, hybrid role detection, public verify page) discussed and documented before implementation. Design system locked in before any component was written. |
| Simplicity | Web3 providers isolated to a (web3) route group layout — root layout stays a pure server component with zero Web3 bundle overhead on the landing page. |
| Feedback | 58 frontend unit/component tests give immediate feedback; TanStack Form's async state behaviour surfaced a latent app bug (missing await on handleSubmit) that would have been invisible in manual testing. |
| Courage | Chose Wagmi v3 + Next.js 16 (both cutting edge at time of writing) and resolved novel issues like the useConnection API and (web3) route group isolation without established precedent. |
| Respect | Every hook and component is documented with programmer name, description, and dates. Test files mirror the same convention, keeping the codebase readable for the examiner and supervisor. |

# BECP — Iteration Plan: Release 2

Phase 2 (Frontend Skeleton + Test Suite)  ·  Week 3–4

## 1. Iteration Goals

- Establish Next.js 16 frontend with (web3) route group isolating all Wagmi/RainbowKit providers

- Implement on-chain role detection (student / organizer / university_admin) via multicall hasRole reads

- Implement off-chain student profile API route + useStudentProfile hook (hybrid auth)

- Deliver fully functional public credential verify page — the one Phase 2 page with live on-chain reads

- Deliver portal shells for all three authenticated roles (student, organizer, admin) with correct routing

- Establish frontend test suite with 58 passing tests across unit, hook, and component layers

## 2. Phase 2A — Foundation & Design System

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Set up Next.js 16 app with TypeScript, Tailwind v4, ShadCN UI | Qayyum | 1.5 | 2 | DONE |
| Configure Wagmi v3 + RainbowKit v2 + TanStack Query in Web3Providers component | Qayyum | 1 | 1.5 | DONE |
| Implement (web3) route group layout isolating providers from root layout | Qayyum | 0.5 | 0.5 | DONE |
| Design and implement globals.css — Syne + DM Sans fonts, teal/amber palette, CSS variables | Qayyum | 1 | 1.5 | DONE |
| Build reusable UI components: Field, FieldGroup, FieldError, InputGroup, PageHeader | Qayyum | 2 | 2 | DONE |
| Build shared layout components: role-specific sidebars (student, organizer, admin) | Qayyum | 1.5 | 2 | DONE |
| Implement BECPLogo SVG component | Qayyum | 0.5 | 0.5 | DONE |

Phase 2A Total — Estimated: 8 hrs  ·  Actual: 10 hrs

## 3. Phase 2B — Authentication & Role Detection

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Implement useRole hook — multicall hasRole for DEFAULT_ADMIN, UNIVERSITY_ADMIN, ISSUER roles | Qayyum | 1 | 1 | DONE |
| Implement useBECPContract hook — centralised address + ABI config for Wagmi call sites | Qayyum | 0.5 | 0.5 | DONE |
| Implement RoleGuard component — redirect to /connect, skeleton while loading, role mismatch redirect | Qayyum | 1 | 1 | DONE |
| Build connect page — RainbowKit ConnectButton, role items display, post-connect role-based redirect | Qayyum | 1 | 1.5 | DONE |
| Implement Hardhat task for granting ISSUER_ROLE to test wallets (Hardhat 3 object-style task API) | Qayyum | 0.5 | 0.5 | DONE |
| Configure lib/wagmi/config.ts — OP Sepolia transport via internal RPC proxy route | Qayyum | 0.5 | 0.5 | DONE |
| Implement /api/rpc/[chain] proxy route to avoid exposing Alchemy key client-side | Qayyum | 0.5 | 1 | DONE |

Phase 2B Total — Estimated: 5 hrs  ·  Actual: 6 hrs

## 4. Phase 2C — Portal Shells & Routing

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Student portal — layout (RoleGuard + StudentSidebar), dashboard overview page with stat cards | Qayyum | 1 | 1 | DONE |
| Student portal — credentials page with category filter buttons (placeholder) | Qayyum | 0.5 | 0.5 | DONE |
| Student portal — events page (placeholder) | Qayyum | 0.5 | 0.5 | DONE |
| Student portal — profile page with ProfileEditForm (TanStack Form, display name, bio, career goal) | Qayyum | 2 | 2.5 | DONE |
| Organizer portal — layout (RoleGuard + OrganizerSidebar), overview page, events page, issue page | Qayyum | 1 | 1 | DONE |
| Admin portal — layout (RoleGuard + AdminSidebar), overview page, organizers page, credentials page | Qayyum | 1 | 1 | DONE |
| Implement landing page — hero section, stats bar, role cards, how-it-works steps, footer | Qayyum | 1.5 | 2 | DONE |

Phase 2C Total — Estimated: 7.5 hrs  ·  Actual: 8.5 hrs

## 5. Phase 2D — Off-Chain Profile & Verify Page

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Implement /api/profile/[address] route — GET + PUT with file-based JSON store (.becp-profiles/) | Qayyum | 1 | 1 | DONE |
| Implement useStudentProfile hook — TanStack Query fetch, cache update on saveProfile mutation | Qayyum | 1 | 1 | DONE |
| Implement VerifyForm using TanStack Form — token ID + address fields, on-chain read via useReadContracts | Qayyum | 1.5 | 2 | DONE |
| Fix VerifyForm submit gate — replace submissionAttempts check with local hasSubmitted useState to ensure re-render in jsdom and browser | Qayyum | 0.5 | 1 | DONE |
| Build public verify page — teal hero background, BECP logo, VerifyForm card, explorer link | Qayyum | 0.5 | 0.5 | DONE |

Phase 2D Total — Estimated: 4.5 hrs  ·  Actual: 5.5 hrs

## 6. Phase 2E — Frontend Test Suite

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Install and configure Vitest + React Testing Library + MSW + jsdom (following Next.js docs) | Qayyum | 0.5 | 1 | DONE |
| Write tests/test-utils.tsx — shared render wrapper, QueryClient factory, Wagmi mock helpers | Qayyum | 0.5 | 0.5 | DONE |
| Write unit tests for /api/profile/[address] route handler — 9 tests (GET + PUT scenarios, fs mock) | Qayyum | 1 | 1 | DONE |
| Write hook tests for useRole — 11 tests (role resolution, loading states, unsupported chain) | Qayyum | 1 | 1 | DONE |
| Write hook tests for useStudentProfile — 7 tests (MSW intercepting fetch, cache update after save) | Qayyum | 1 | 1.5 | DONE |
| Write component tests for RoleGuard — 7 tests (skeleton, redirect, children render) | Qayyum | 0.5 | 0.5 | DONE |
| Write component tests for VerifyForm — 12 tests (validation, submit gate, result states) | Qayyum | 1.5 | 3 | DONE |
| Write component tests for ProfileEditForm — 10 tests (population, dirty state, save interactions) | Qayyum | 1 | 1.5 | DONE |
| Debug: TanStack Form async handleSubmit does not re-render in jsdom — fix via hasSubmitted useState | Qayyum | — | 1.5 | DONE |
| Debug: fake timers conflict with userEvent default setup — fix via advanceTimers in beforeEach | Qayyum | — | 0.5 | DONE |
| All 58 tests passing ✓ | Qayyum | — | — | DONE |

Phase 2E Total — Estimated: 7 hrs  ·  Actual: 11 hrs

Release 2 Total — Estimated: 32 hrs  ·  Actual: 41 hrs

## 7. Retrospective Notes

| Category | Note |
| --- | --- |
| Went well | The (web3) route group pattern cleanly isolated Wagmi providers from the root layout. The landing page ships zero Web3 JS — a meaningful performance win for the recruiter entry point. |
| Went well | TanStack Form's field-level validation and dirty state tracking made ProfileEditForm significantly cleaner than a manual useState approach would have been. |
| Went well | MSW for useStudentProfile hook tests was more robust than mocking fetch directly — it catches URL construction bugs that vi.fn() mocks would silently pass. |
| Went over | Testing TanStack Form components with Vitest + jsdom took 3x the estimated time. The async handleSubmit state update not triggering a re-render in jsdom required diagnosing with console.log instrumentation and replacing the submissionAttempts check with a local useState boolean. |
| Went over | Fake timers conflicting with userEvent required moving userEvent.setup() into beforeEach with advanceTimers: vi.advanceTimersByTime.bind(vi) — a non-obvious fix that added half an hour. |
| Went over | Design system and sidebar components took longer than estimated due to Tailwind v4 configuration differences from v3 (PostCSS plugin instead of tailwind.config.js). |
| Learned | When a test fails with 'element not found' for a result panel, the first question should be whether the form's isValid gate is correctly set before submission — not whether the component itself is broken. |
| Action item | For Phase 3: add SIWE (Sign-In With Ethereum) authentication to the profile API before connecting organizer issuance — the current unauthenticated PUT endpoint is acceptable for Phase 2 but not for write operations involving on-chain actions. |
| Action item | For Phase 3: establish the useReadContract pattern for balanceOf and getStudentCredentials before building the credential gallery UI component. |

# BECP — User Stories: Release 2

Phase 2 (Frontend Skeleton)  ·  US-09 through US-14  ·  All stories verified by passing test suite

## US-09 — All Users

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-09 | All Users | Must Have | R2 / Phase 2B | DONE |
| --- | --- | --- | --- | --- |

Story:

"As any user, I want to connect my Ethereum wallet to the BECP platform so that I am authenticated and redirected to the correct portal for my role."

Acceptance Criteria:

- ✓  RainbowKit ConnectButton renders on the /connect page supporting MetaMask, Rainbow, and WalletConnect

- ✓  On successful connection, useRole reads hasRole for DEFAULT_ADMIN, UNIVERSITY_ADMIN, and ISSUER roles in a single multicall

- ✓  Role resolution order: DEFAULT_ADMIN and UNIVERSITY_ADMIN_ROLE → university_admin, ISSUER_ROLE → organizer, none → student

- ✓  University admin role takes precedence over organizer even if both roles are held

- ✓  User is redirected to /dashboard, /organizer, or /admin based on resolved role

- ✓  While role is loading (isReconnecting or isConnecting), a branded skeleton screen is shown

- ✓  Recruiter path: a link on the connect page navigates directly to /verify with no wallet required

Test coverage: useRole.test.ts — 11 tests; RoleGuard.test.tsx — 7 tests

## US-10 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-10 | Student | Must Have | R2 / Phase 2C | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a student, I want to see a dashboard overview of my credential portfolio so that I have a quick summary of my achievements and skill development."

Acceptance Criteria:

- ✓  Dashboard page renders within the student portal protected by RoleGuard(['student'])

- ✓  A personalised greeting uses the student's display name from their off-chain profile, falling back to a truncated wallet address

- ✓  Four stat cards are displayed: Credentials, Skills tracked, Activity hours, Events joined (showing — as empty state)

- ✓  Two placeholder sections are visible: Skill Progress (based on career goal) and Recent Credentials

- ✓  Non-student wallets connecting to /dashboard are redirected to their correct portal

Test coverage: RoleGuard.test.tsx — redirect tests; useStudentProfile.test.ts — displayName fallback test

## US-11 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-11 | Student | Must Have | R2 / Phase 2D | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a student, I want to set my display name, bio, and career goal so that my public credential portfolio shows accurate personal information to recruiters."

Acceptance Criteria:

- ✓  Profile edit form renders on /dashboard/profile with fields for display name (max 60 chars), bio (max 280 chars), and a career goal dropdown

- ✓  Form is pre-populated from the fetched off-chain profile on load; a skeleton is shown while loading

- ✓  Save button is disabled when the form is not dirty; an 'Up to date' indicator is shown when clean

- ✓  On save, displayName and bio are trimmed of whitespace before persisting

- ✓  PUT /api/profile/:address upserts the profile JSON file — preserving existing fields not included in the update

- ✓  A success toast is shown after saving; an error toast is shown if the save fails

- ✓  Wallet address field is shown read-only with a 'Read-only' badge — it cannot be edited

- ✓  A privacy notice informs the student that profile data is off-chain and all fields are optional

Test coverage: ProfileEditForm.test.tsx — 10 tests; api-profile.test.ts — 9 tests; useStudentProfile.test.ts — 7 tests

## US-12 — Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-12 | Organizer | Must Have | R2 / Phase 2C | DONE |
| --- | --- | --- | --- | --- |

Story:

"As an approved event organizer, I want to access the organizer portal so that I can manage my events and issue credentials to participants."

Acceptance Criteria:

- ✓  Organizer portal is accessible at /organizer and protected by RoleGuard(['organizer'])

- ✓  Overview page shows four stat cards: Active Events, Credentials issued, Participants, Credential Types

- ✓  Navigation sidebar provides links to Overview, My Events, and Issue Credentials sections

- ✓  Issue credentials page displays the three-step issuance flow (Select Type, Add Recipients, Review & Issue) as placeholder cards

- ✓  An info alert on the issue page explains the on-chain action and ISSUER_ROLE requirement

- ✓  Wallets without ISSUER_ROLE attempting to access /organizer are redirected to their correct portal

Test coverage: RoleGuard.test.tsx — role mismatch redirect tests

## US-13 — University Admin

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-13 | University Admin | Must Have | R2 / Phase 2C | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a university admin, I want to access the admin portal so that I can manage organizer approvals and monitor platform-wide credential activity."

Acceptance Criteria:

- ✓  Admin portal is accessible at /admin and protected by RoleGuard(['university_admin'])

- ✓  Overview page shows four stat cards: Active Organizers, Total Credentials, Students onboarded, Pending approvals

- ✓  Navigation sidebar links to Overview, Organizer Management, and Credentials Overview

- ✓  Organizer management page shows Pending Approvals and Active Organizers sections with an on-chain action info alert

- ✓  Credentials overview page shows three platform-wide stats and an Emergency Controls section with a Pause Platform button

- ✓  DEFAULT_ADMIN_ROLE wallets are treated as university_admin and gain full admin portal access

- ✓  Non-admin wallets attempting to access /admin are redirected to their correct portal

Test coverage: RoleGuard.test.tsx — role mismatch redirect tests; useRole.test.ts — DEFAULT_ADMIN precedence test

## US-14 — Recruiter

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |

| US-14 | Recruiter | Must Have | R2 / Phase 2D | DONE |
| --- | --- | --- | --- | --- |

Story:

"As a recruiter, I want to verify a candidate's credential on-chain using a token ID and wallet address so that I can confirm the credential is authentic without needing a blockchain wallet."

Acceptance Criteria:

- ✓  Verify page at /verify is publicly accessible — no wallet connection required

- ✓  Form accepts a Token ID (numeric) and Holder Wallet Address (Ethereum address) with inline validation

- ✓  Token ID field shows an error after blur if the value is non-numeric

- ✓  Address field shows an error after blur if the value is not a valid Ethereum address

- ✓  Submit button is disabled while fields are invalid or the query is loading

- ✓  On submit, balanceOf(address, tokenId) and uri(tokenId) are read from the BECPCredential contract on OP Sepolia

- ✓  A green 'Credential Verified' panel is shown when balance > 0, displaying token ID, holder address, network, and links to the block explorer and IPFS metadata

- ✓  A red 'Credential Not Found' alert is shown when balance is 0 or the token ID does not exist

- ✓  An amber 'Network error' alert is shown when the RPC call fails

- ✓  Token ID and wallet address can be pre-filled via ?tokenId=N&address=0x... URL query parameters

Test coverage: VerifyForm.test.tsx — 12 tests

# BECP — CRC Cards: Frontend Layer

Component Responsibility Collaborator cards for Phase 2 frontend architecture

| useRole · Custom Hook (Auth) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Read DEFAULT_ADMIN_ROLE, UNIVERSITY_ADMIN_ROLE, and ISSUER_ROLE from BECPCredential in a single multicall - Resolve role precedence: university_admin > organizer > student - Expose isLoading flag combining isReconnecting, isConnecting, and contract read loading states - Return isConnected, isAdmin, isUniversityAdmin, isOrganizer, isStudent flags for consumer convenience - Gracefully handle missing contract address (unsupported chain) by falling back to student role | - useBECPContract (address + ABI source) - useReadContracts / useConnection / useChainId (Wagmi v3) - RoleGuard (primary consumer) - ConnectPage (role-based redirect after connect) - @becp/shared CONTRACT_ROLES constants |

| useBECPContract · Custom Hook (Contract Config) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Return a stable { address, abi } config object for spreading into Wagmi contract call hooks - Resolve deployed contract address from chain ID via getContractAddress() - Return null when no contract is deployed on the current chain - Centralise ABI import so no call site imports it directly | - useChainId (Wagmi v3) - getContractAddress / BECP_CREDENTIAL_ABI (@becp/shared/contract) - useRole (consumer) - VerifyForm (consumer) |

| useStudentProfile · Custom Hook (Off-Chain Data) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Fetch student profile from /api/profile/:address using TanStack Query - Expose saveProfile mutation that PUTs updated fields and updates the query cache on success - Derive displayName with fallback to truncated wallet address when profile has no displayName - Keep profile data stale for 5 minutes — profile changes are infrequent - Skip fetch when no wallet is connected (address is undefined) | - useConnection (Wagmi v3 — provides connected address) - useQuery / useMutation / useQueryClient (TanStack Query v5) - /api/profile/[address] route (data source) - ProfileEditForm (primary consumer) - DashboardPage (displayName consumer) |

| RoleGuard · Component (Access Control) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Redirect unauthenticated users to /connect - Show a branded loading skeleton while role is being resolved - Redirect authenticated users whose role is not in allowedRoles to their correct portal home - Render children only when role matches and wallet is connected | - useRole (role resolution source) - useRouter (Next.js navigation for redirects) - BECPLogo / Spinner (skeleton UI) - @becp/shared ROUTES constants - All three portal layouts (consumer) |

| VerifyForm · Component (Public Verification) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Accept token ID (numeric) and holder address (Ethereum) inputs with field-level validation - Gate on-chain reads behind a hasSubmitted flag to ensure React re-renders before querying - Read balanceOf and uri from BECPCredential via useReadContracts on form submission - Derive verification status (idle / loading / valid / invalid / error) from query state - Display role-appropriate result panels: verified success, not found, network error - Support URL query param pre-fill for shareable verification links | - useForm (TanStack Form v1) - useReadContracts (Wagmi v3) - BECP_CREDENTIAL_ABI / CHAIN / ipfsToHttp (@becp/shared) - Field / FieldGroup / Input / Button / Alert / Card (ShadCN UI) - Spinner (UI component) |

| ProfileEditForm · Component (Student Profile) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Pre-populate form fields from fetched profile using useEffect on profile load - Manage display name, bio, and career goal fields with TanStack Form - Track dirty state — save button enabled only when form has unsaved changes - Trim whitespace from display name and bio before persisting - Show success or error toast based on saveProfile mutation outcome - Show skeleton placeholders while profile is loading | - useStudentProfile (data + mutation source) - useForm (TanStack Form v1) - toast (Sonner) - Field / Input / InputGroup / Select / Button / Alert / Skeleton (ShadCN UI) |

| /api/profile/[address] · API Route (Next.js) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - GET: return stored profile JSON for a given wallet address, or 404 if not found - PUT: upsert profile JSON — preserving fields not included in the request body - Validate address with viem isAddress before any file I/O - Normalise address to lowercase before using as a filename key - Set createdAt on first creation; always update updatedAt on PUT - Store profiles as individual JSON files under .becp-profiles/ (PoC — to be migrated to database in Phase 4) | - fs/promises (Node.js file I/O) - isAddress (viem validation) - NextRequest / NextResponse (Next.js) - useStudentProfile (HTTP client) |