# BECP — XP Release Plan (Updated: Release 3)

Blockchain-based Extracurricular Credentials Platform  ·  TP075129  ·  APU BSc Software Engineering

Project dates: March 2026 – June 2026  ·  Methodology: Extreme Programming (XP)  ·  Developer: Muhammad Qayyum bin Mahamad Yazid

## 1. Project Overview

BECP is a blockchain-based credential platform issuing soulbound ERC-1155 NFT micro-credentials to university students upon completing extracurricular activities. The system serves four roles — students, organizers, university administrators, and HR recruiters — deployed on Optimism L2. Release 3 delivers the full credential lifecycle on the organizer side (type registration and batch issuance) and the complete student credential dashboard with a gamified skill progression system. Phases 3C and 3D were pulled forward from the planned R4 scope after R3 Phase 3A–3B work was completed ahead of schedule.

## 2. Release Summary

| Release | Phase(s) | Deliverable | Target | Status |
| --- | --- | --- | --- | --- |
| R1 | Phase 0 + 1 | Monorepo scaffold + ERC-1155 soulbound smart contract + 52 passing tests + Hardhat 3 deployment config | Week 1–2 | DONE |
| R2 | Phase 2 | Next.js 16 frontend skeleton — wallet auth (RainbowKit), on-chain role detection, routing for all 4 user types, off-chain student profile API, functional verify page, frontend test suite (58 tests) | Week 3–4 | DONE |
| R3 | Phase 3A–3D | Credential type registration + batch issuance (organizer) + credential gallery + skill progression dashboard (student) — 57 new tests, 115 total | Week 5–7 | DONE |
| R4 | Phase 3E–3F | Recruiter QR verification portal + exportable credential portfolio PDF | Week 8–9 | PENDING |
| R5 | Phase 3G | OP Mainnet production deployment + end-to-end hardening | Week 10 | PENDING |

## 3. XP Values Applied in Release 3

| XP Value | How it manifests in Release 3 |
| --- | --- |
| Communication | Multi-step flows (credential registration, issuance wizard) were designed end-to-end before implementation — wallet call sequence, IPFS pinning, event log parsing, and toast feedback all agreed on paper first. |
| Simplicity | parseRecipients kept as a pure inline function rather than a separate module — no abstraction overhead for logic used in exactly one place. Skill score formula (duration × weight) kept simple and transparent. |
| Feedback | 57 new unit and hook tests give immediate feedback on the credential pipeline and skill aggregation logic. The wagmi mock argument-forwarding bug was caught immediately by the useOrganizerCredentialTypes test suite. |
| Courage | Chose to pull Phases 3C and 3D forward into R3 ahead of schedule, and integrated Recharts charts into shadcn ChartContainer without established precedent — resolved the CSS variable injection pattern through direct library exploration. |
| Respect | All source files carry the full programmer header convention. Test files replicate the same header, ensuring the examiner and supervisor can trace every file to its author and purpose. |

# BECP — Iteration Plan: Release 3

Phase 3A–3D + Test Suite  ·  Week 5–7

## 1. Iteration Goals

- Deliver the full organizer credential issuance flow: type registration → IPFS metadata upload → on-chain mint

- Deliver the student credential gallery: wallet token IDs → IPFS metadata hydration → filterable card grid

- Deliver the gamified skill progression dashboard: bar chart (career-goal-aware priority ordering) + soft skills radar

- Establish the shared SKILL_POOL and CAREER_GOAL_SKILLS constants as single sources of truth

- 57 new tests passing (21 unit + 13 + 23 hook tests) — 115 total across the frontend suite

## 2. Phase 3A — Organizer Credential Type Registration

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Define SKILL_POOL in shared/constants/skill-pool.ts — 23 skills across 5 categories (technical, soft, leadership, creative, domain) with per-skill weights; export SKILL_POOL_BY_ID Map for O(1) lookup | Qayyum | 1 | 1 | DONE |
| Implement lib/credential/metadata.ts — CredentialTypeMetadata interface (ERC-1155/OpenSea + Open Badges 3.0 alignment + BECP custom fields), buildCredentialTypeMetadata(), uploadCredentialTypeMetadata() fetching /api/metadata | Qayyum | 1 | 1 | DONE |
| Implement /api/metadata POST route — accepts JSON body, pins to Pinata under a derived filename, returns { cid, uri }; Pinata JWT kept server-side | Qayyum | 0.5 | 0.5 | DONE |
| Configure lib/pinata/config.ts — Pinata SDK client reading PINATA_JWT from env | Qayyum | 0.5 | 0.5 | DONE |
| Implement useOrganizerCredentialTypes hook — 5-step pipeline: totalCredentialTypes() → tokenIds → batch getCredentialType() → filter by issuer address → batch totalSupply() → useQueries for IPFS metadata; expose HydratedCredentialType[], OrganizerStats, isLoading, isError, refetch | Qayyum | 2 | 2.5 | DONE |
| Build credential-type-form.tsx — TanStack Form with name, description, activity date (date picker), category (select), duration hours, issuer name, external URL, and multi-select skill picker reading from SKILL_POOL; field-level validation; disabled submit while submitting | Qayyum | 2 | 3 | DONE |
| Build credential-type-card.tsx — card showing credential type name, token ID badge, category badge, activity date, duration, skill tags, issued count, and an Issue Credentials shortcut link; CredentialTypeCardSkeleton for loading state | Qayyum | 1 | 1 | DONE |
| Build organizer/events/page.tsx — list/create view toggle (URL ?view= param); handleRegister: build metadata → upload to IPFS → registerCredentialType → waitForTransactionReceipt → parseEventLogs for CredentialTypeRegistered → extract tokenId; empty state and error alert | Qayyum | 1.5 | 2 | DONE |

Phase 3A Total — Estimated: 9.5 hrs  ·  Actual: 11.5 hrs

## 3. Phase 3B — Organizer Batch Issuance

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Implement inline parseRecipients utility — splits textarea input by newlines, trims whitespace, filters blanks, validates with viem isAddress, deduplicates case-insensitively using a normalised Set; returns ParsedRecipient[] with raw, address, isValid, isDuplicate fields | Qayyum | 0.5 | 0.5 | DONE |
| Build StepIndicator component — 3-step horizontal progress indicator with done/active/pending states; responsive (step labels hidden on small screens) | Qayyum | 0.5 | 0.5 | DONE |
| Build CredentialTypeSelector sub-component — clickable card list of active credential types with metadata preview (name, token ID, category, date, duration); loading skeleton; empty state when no active types | Qayyum | 1 | 1 | DONE |
| Build RecipientInput sub-component — Textarea with live parseRecipients feedback: valid count (green), invalid count (red), duplicate count (amber), total count; per-line error/warning messages below the input | Qayyum | 1 | 1.5 | DONE |
| Build ReviewPanel sub-component — credential type summary card + scrollable recipient address list + transaction summary ('1 transaction will mint N soulbound credentials on OP Sepolia'); on-chain action info alert with ISSUER_ROLE note | Qayyum | 0.5 | 0.5 | DONE |
| Wire batchIssueCredential on Step 3 — useWriteContract mutateAsync → waitForTransactionReceipt → parseEventLogs for CredentialIssued count → success toast with block explorer link; isIssuing loading state disables Back/Issue buttons | Qayyum | 1 | 1.5 | DONE |
| Support ?tokenId= URL param — if a valid active tokenId is passed via search params, skip to Step 2 with that type pre-selected; show toast warning if tokenId not found or inactive | Qayyum | 0.5 | 0.5 | DONE |

Phase 3B Total — Estimated: 5 hrs  ·  Actual: 6 hrs

## 4. Phase 3C — Student Credential Gallery

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Implement useStudentCredentials hook — pipeline: getStudentCredentials(address) → useMemo-stabilised ids → batch uri(tokenId) reads → useQueries IPFS metadata fetch (retry: 2, 10-min staleTime) → HydratedCredential[]; aggregate AggregatedSkillScore[] via score = durationHours × weight per skill ID; derive StudentStats (totalCredentials, totalActivityHours, uniqueSkillCount, categoryBreakdown) | Qayyum | 2 | 2.5 | DONE |
| Build credential-card.tsx — CredentialCard showing name, token ID badge, category badge, description (line-clamp-2), activity date, duration, issuer name, skill tags with colour-coded category classes and weight multipliers; CredentialCardSkeleton for loading state; footer: Verify link, Explorer link, IPFS Metadata link | Qayyum | 1 | 1 | DONE |
| Build (student)/dashboard/credentials/page.tsx — SkillScoreSummary (4 stat cards); TopSkillsPreview pill row; category filter buttons (only populated categories shown, with counts); 3-column credential card grid; error alert with Retry; empty states; 3 skeleton cards while loading | Qayyum | 2 | 2 | DONE |

Phase 3C Total — Estimated: 5 hrs  ·  Actual: 5.5 hrs

## 5. Phase 3D — Student Skill Dashboard

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Define shared/constants/career-goals.ts — CAREER_GOAL_SKILLS mapping 14 career goal strings to ordered priority skill ID arrays; getPrioritySkillIds(careerGoal) helper returning [] for Other/unrecognised | Qayyum | 0.5 | 1 | DONE |
| Build skill-progress-chart.tsx — BarChart inside shadcn ChartContainer; ChartConfig maps skill keys to SKILL_LEVELS colour CSS variables; priority skills first (with zeroScore placeholders for unearned); non-priority skills at 45% opacity; custom bar shape reading var(--color-<skillKey>); dashed ReferenceLine at nextLevelThreshold; custom SkillTooltipContent | Qayyum | 2 | 3 | DONE |
| Build soft-skills-radar-chart.tsx — RadarChart inside shadcn ChartContainer; all 6 soft skills always shown (zeroSoftScore placeholders for unearned); normalised against Expert threshold (700 pts); custom SoftSkillTooltipContent | Qayyum | 1 | 1.5 | DONE |
| Build recent-credentials-list.tsx — compact list of up to maxItems (default 5) credentials with award icon, name (truncated), token ID, category badge; View all N link when list exceeds maxItems; skeleton and empty states | Qayyum | 0.5 | 0.5 | DONE |
| Update (student)/dashboard/page.tsx — live stat cards from useStudentCredentials; split skillScores into technicalSkillScores (bar chart) and softSkillScores (radar chart); pass prioritySkillIds from getPrioritySkillIds(careerGoal); career-goal-aware CardDescription; always-visible soft skills card; footer nudge linking to profile page when no career goal set | Qayyum | 1.5 | 2 | DONE |

Phase 3D Total — Estimated: 5.5 hrs  ·  Actual: 8 hrs

## 6. Phase 3E — Frontend Test Suite

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Write tests/unit/parseRecipients.test.ts — 21 pure unit tests (no DOM/Wagmi); covers empty input, valid/invalid addresses, case-insensitive duplicate detection, canProceedStep2 guard; replicates parseRecipients verbatim as deliberate regression signal | Qayyum | 1 | 1 | DONE |
| Write tests/hooks/useOrganizerCredentialTypes.test.ts — 13 hook tests; wagmi mocked via vi.mock; MSW intercepts IPFS fetch; covers loading/error states, issuer filtering (case-insensitive), issuedCount from totalSupply, aggregate stats, IPFS metadata hydration; useReadContracts mocked via mockImplementation dispatching on contracts[0].functionName to avoid desync | Qayyum | 1.5 | 2 | DONE |
| Write tests/hooks/useStudentCredentials.test.ts — 23 hook tests; covers disconnected wallet, loading/error states, credential hydration, skill score formula (score = durationHours × weight), cross-credential accumulation, descending sort, all four skill levels, nextLevelThreshold null for Expert, progressPercent, StudentStats, ids useMemo stability | Qayyum | 2 | 2.5 | DONE |
| Debug and fix test failures: guard issuer?.toLowerCase() in useOrganizerCredentialTypes; switch to mockImplementation for useReadContracts to fix mock desync; fix waitFor callbacks to use expect (throws) rather than returning booleans; wait on isMetadataLoading per-credential for IPFS failure tests | Qayyum | 1 | 1.5 | DONE |

Phase 3E Total — Estimated: 5.5 hrs  ·  Actual: 7 hrs

Release 3 Total — Estimated: 30.5 hrs  ·  Actual: 38 hrs

## 7. Retrospective Notes

| Category | Note |
| --- | --- |
| Went well | The shadcn ChartContainer + Recharts combination produced clean, theme-consistent charts. Understanding that ChartConfig keys become --color-<key> CSS variables (injected by ChartContainer) unlocked the level-based bar colouring approach without any custom CSS. |
| Went well | Pulling Phases 3C and 3D into R3 ahead of schedule was viable because useStudentCredentials closely mirrored the useOrganizerCredentialTypes pipeline — both use the same multi-step read → filter → useQueries IPFS hydration pattern, so the second hook took significantly less time than the first. |
| Went well | Zero-score placeholder approach for priority skills in the bar chart was minimal to implement: the hook already computes skill scores; the chart component adds placeholders only at render time by reading SKILL_POOL_BY_ID, requiring no hook changes. |
| Went over | CredentialTypeForm took longer than estimated. The skill multi-selector (picking from 23 SKILL_POOL entries with category grouping, weight display, and remove-on-click) required careful TanStack Form field-array wiring and more UI work than a standard text input. |
| Went over | useStudentCredentials skill aggregation grew in scope mid-implementation: the initial plan was a simple score sum, but adding AggregatedSkillScore (with level, progressPercent, nextLevelThreshold) for the dashboard charts required scoreToLevel() and shared SKILL_LEVELS to be co-designed with the hook. |
| Went over | Recharts BarChart custom bar colouring via the shape prop (custom SVG <rect>) was not documented clearly. Discovering that bar fill must read var(--color-<skillKey>) and that the key must be kebab-case and match ChartConfig exactly added ~1hr of debugging. |
| Learned | When a wagmi hook (useReadContracts) is called multiple times per render with different arguments, mockReturnValueOnce desynchronises on re-renders. The correct pattern is mockImplementation dispatching on contracts[0]?.functionName. |
| Action item | For R4/Phase 3E: QR code generation on credential cards. The /verify page already handles on-chain verification; only the QR library integration and shareable URL generation remain. |
| Action item | For R4: Add SIWE (Sign-In With Ethereum) to the /api/profile PUT route before any write-protected organizer API endpoints are introduced. |

# BECP — User Stories: Release 3

Phase 3A–3D  ·  US-15 through US-18  ·  All stories verified by passing test suite

## US-15 — Event Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-15 | Event Organizer | Must Have | R3 / Phase 3A | DONE |

"As an approved event organizer, I want to register a credential type with full event metadata and skill tags so that I can later batch-issue it to participants as an on-chain soulbound credential."

Acceptance Criteria:

- ✓ Organizer accesses the credential type registration form from the My Events page

- ✓ Form collects: credential name, description, activity date (date picker), activity category (select from predefined list), duration in hours, organizer/issuer display name, optional external URL, and one or more skill tags (multi-select from the shared SKILL_POOL of 23 skills)

- ✓ On submit, metadata is built locally (buildCredentialTypeMetadata) and pinned to IPFS via /api/metadata, receiving an ipfs:// URI

- ✓ registerCredentialType(uri) is called on the BECPCredential contract; the connected wallet must hold ISSUER_ROLE

- ✓ Toast notifications show: "Uploading metadata…", "Waiting for wallet signature…", "Waiting for confirmation…", then success with the assigned token ID extracted from CredentialTypeRegistered event logs

- ✓ The new credential type appears immediately in the My Events list after successful registration

- ✓ The form disables all inputs and shows a spinner during submission

Test coverage: useOrganizerCredentialTypes.test.ts — IPFS metadata hydration and issuer filtering

## US-16 — Event Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-16 | Event Organizer | Must Have | R3 / Phase 3B | DONE |

"As an approved event organizer, I want to issue credentials to a list of participant wallet addresses in a single transaction so that all participants receive their NFT certificate at once."

Acceptance Criteria:

- ✓ Step 1: Organizer selects one of their active credential types from a card list; inactive types are hidden

- ✓ Step 2: Organizer enters recipient wallet addresses (one per line); each line is validated with viem isAddress; invalid lines show red error messages; duplicate addresses show amber warnings and are excluded from the final list

- ✓ The Next button on Step 2 is disabled until at least one valid non-duplicate address is entered

- ✓ Step 3: Review panel shows the credential type summary and full recipient list; an info alert explains this is an on-chain ISSUER_ROLE action

- ✓ Clicking Issue calls batchIssueCredential(tokenId, validRecipients[]); success toast shows issued count and links to the block explorer transaction

- ✓ If a ?tokenId= query param is present and matches an active credential type, the page opens at Step 2 with that type pre-selected

Test coverage: parseRecipients.test.ts — 21 unit tests covering address validation and duplicate detection

## US-17 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-17 | Student | Must Have | R3 / Phase 3C | DONE |

"As a student, I want to see all of my on-chain credentials in a gallery so that I can review what I have earned and share them."

Acceptance Criteria:

- ✓ The gallery reads getStudentCredentials(address) to get all token IDs held by the connected wallet, then fetches uri(tokenId) and IPFS metadata for each

- ✓ Each credential is shown as a card with: name, token ID badge, category badge, description (2 lines), activity date, duration, issuer name, and skill tags with category colours and weight multipliers

- ✓ Skeleton cards are shown while credential data is loading

- ✓ Filter buttons appear for each activity category that has at least one credential; the All button shows the total count

- ✓ An empty state is shown when the student holds no credentials; a filtered empty state is shown when the active filter returns no results

- ✓ An error alert with a Retry button is shown if the blockchain read fails

- ✓ Each card has footer links: Verify (pre-fills /verify?tokenId=), Block Explorer, and IPFS Metadata

Test coverage: useStudentCredentials.test.ts — credential hydration, tokenURI mapping, error states

## US-18 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-18 | Student | Must Have | R3 / Phase 3D | DONE |

"As a student, I want to see my aggregated skill scores and progression level so that I can understand which skills I am developing through my extracurricular activities."

Acceptance Criteria:

- ✓ The dashboard shows four live stat cards: total credentials (on-chain), unique skills tracked, total activity hours, and advanced+ skill count

- ✓ A "Skill Progress" bar chart shows aggregated skill scores (score = Σ durationHours × weight across all credentials for that skill); bars are coloured by level using the SKILL_LEVELS colour palette

- ✓ If the student has set a career goal, priority skills for that goal appear first in the chart (with zero-score placeholder bars if not yet earned); non-priority skills appear after at 45% opacity

- ✓ The chart includes a dashed reference line marking the next level threshold for the leading skill

- ✓ A custom tooltip shows: skill label, category, level badge with score, pts to next level, progress percent, and source credential count

- ✓ A level legend below the chart identifies the colour for each of the four levels (Beginner 0+, Intermediate 100+, Advanced 300+, Expert 700+)

- ✓ A "Soft Skills" radar chart is always shown regardless of career goal, with all 6 soft skill axes displayed; unearned skills show at zero; radar is normalised against the Expert threshold (700 pts)

- ✓ A "Recent Credentials" sidebar shows the 5 most recent credentials with name, token ID, and category badge; a "View all N credentials" link appears when there are more than 5

- ✓ A footer prompt on the Soft Skills card links to the profile page to encourage setting a career goal when none is set

- ✓ Skill progress and radar charts show skeleton placeholders while credential data is loading

Test coverage: useStudentCredentials.test.ts — skill score computation, level derivation, nextLevelThreshold null for Expert, progressPercent

# BECP — CRC Cards: Release 3 Frontend & Shared Layer

Component Responsibility Collaborator cards for the Phase 3A–3D frontend architecture

| SKILL_POOL / SKILL_POOL_BY_ID · Shared Constants |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Provide a single source of truth for all 23 platform skills across 5 categories (technical, soft, leadership, creative, domain) with ID, label, category, and weight - Export SKILL_POOL (array) for iteration and multi-select UI components - Export SKILL_POOL_BY_ID (Map) for O(1) skill lookup by ID in hooks and chart components - Provide category-level grouping for radar chart axis selection (all soft skills) | - shared/constants/skill-pool.ts (definition) - CredentialTypeForm (organizer skill picker) - useStudentCredentials (score aggregation) - SkillProgressChart, SoftSkillsRadarChart (zero-score placeholders) |

| CAREER_GOAL_SKILLS / getPrioritySkillIds · Shared Constants |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Map each of the 14 career goal options to an ordered list of priority skill IDs (most important first) - Export getPrioritySkillIds(careerGoal) returning [] for 'Other' or unrecognised goals - Drive the bar chart's priority ordering — skills listed first appear first with zero-score placeholders for unearned ones - Reserved for Phase 4 AI skill recommendation augmentation — static lookup for Phase 3 | - shared/constants/career-goals.ts (definition) - useStudentProfile (careerGoal source) - SkillProgressChart (priority ordering) - DashboardPage (prioritySkillIds derivation) |

| lib/credential/metadata · Library (Metadata Builder) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Define CredentialTypeMetadata interface combining ERC-1155/OpenSea standard fields, Open Badges 3.0 alignment fields, and BECP-custom fields (becp_version, becp_issuer_*, becp_activity_*, becp_skills) - buildCredentialTypeMetadata(input) — assembles the metadata object from form values; formats activityDate to ISO 8601; uses a placeholder badge image until Phase 4 artwork upload - uploadCredentialTypeMetadata(metadata) — POSTs to /api/metadata and returns the ipfs:// URI; throws on non-OK responses - Keep credential type metadata construction pure and testable, separate from the UI layer | - OrganizerEventsPage (build + upload call site) - useOrganizerCredentialTypes (CredentialTypeMetadata type consumer) - /api/metadata route (upload target) - useStudentCredentials (CredentialTypeMetadata type consumer for hydrated data) |

| /api/metadata · API Route (IPFS Proxy) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Accept a JSON POST body representing a CredentialTypeMetadata document - Pin the JSON to Pinata under a derived filename (becp-credential-<n>.json) using the Pinata SDK - Return { cid, uri } where uri = ipfs://<cid> — the URI used in registerCredentialType() - Keep the Pinata JWT server-side — never exposed to the browser | - lib/credential/metadata.ts (HTTP client via uploadCredentialTypeMetadata) - lib/pinata/config.ts (Pinata SDK client) - Pinata (external IPFS storage) - OrganizerEventsPage (result consumer) |

| useOrganizerCredentialTypes · Custom Hook |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Read totalCredentialTypes() to determine the token ID range (1..N) - Batch-read getCredentialType(id) for all IDs; filter results to those where issuer === connected address (case-insensitive); guard against undefined issuer from malformed results - Batch-read totalSupply(id) for owned types to derive issuedCount per credential type - Fetch IPFS metadata for each owned type via useQueries with retry: 2 and 5-min staleTime - Expose HydratedCredentialType[], OrganizerStats (totalTypes, activeTypes, totalIssued), isLoading, isError, refetch | - useBECPContract (address + ABI source) - useReadContract / useReadContracts / useConnection (Wagmi v3) - useQueries (TanStack Query v5 — IPFS metadata) - ipfsToHttp / CredentialTypeMetadata (@becp/shared) - OrganizerEventsPage, OrganizerIssuePage (consumers) |

| useStudentCredentials · Custom Hook |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Read getStudentCredentials(address) to get all token IDs held by the connected wallet; stabilise the ids reference with useMemo to prevent unnecessary re-renders - Batch-read uri(tokenId) for all held IDs; fetch IPFS metadata per URI via useQueries - Aggregate skill scores: for each credential with metadata, iterate becp_skills and accumulate score = durationHours × weight per skill ID - Derive skill level (beginner/intermediate/advanced/expert) and progressPercent/nextLevelThreshold per aggregated score using scoreToLevel() and SKILL_LEVELS - Compute StudentStats: totalCredentials (from token IDs), totalActivityHours, uniqueSkillCount, categoryBreakdown - Sort AggregatedSkillScore[] by totalScore descending for bar chart and top-skills preview | - useBECPContract (address + ABI source) - useReadContract / useReadContracts / useConnection (Wagmi v3) - useQueries (TanStack Query v5 — IPFS metadata) - SKILL_LEVELS / scoreToLevel / SKILL_POOL_BY_ID (@becp/shared) - CredentialsPage, DashboardPage (consumers) - SkillProgressChart, SoftSkillsRadarChart (skill score consumers) |

| CredentialTypeForm · Component (Organizer) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Collect all credential type registration fields via TanStack Form: name, description, activity date (shadcn Calendar), category (Select from ACTIVITY_CATEGORIES), duration hours, issuer name, optional external URL - Provide a skill multi-select that reads from SKILL_POOL — organizer selects skills by category; selected skills show as removable tags with weight displayed - Validate fields: name and description required; activityDate required; durationHours must be a positive integer; at least one skill required - Call onSubmit(values) provided by the parent page; disable the submit button and show a spinner while submission is in progress | - useForm (TanStack Form v1) - SKILL_POOL (@becp/shared — skill source) - Field / Select / Calendar / Button (ShadCN UI) - OrganizerEventsPage (submit handler) |

| CredentialTypeCard · Component (Organizer) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Display a credential type's name, token ID badge, active/inactive status badge, activity category, date, duration, and skill tags - Show issued count (totalSupply) as a badge — updates after each batch issuance - Provide an 'Issue Credentials' shortcut button that links to /organizer/issue?tokenId=<id> - Show CredentialTypeCardSkeleton (3 skeleton cards) while useOrganizerCredentialTypes is loading | - HydratedCredentialType (useOrganizerCredentialTypes — data source) - OrganizerEventsPage (renders card list) - Card / Badge / Button (ShadCN UI) |

| parseRecipients · Inline Utility (Organizer Issue Page) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Split raw textarea input by newlines; trim whitespace; filter blank lines - Validate each line with viem isAddress; return isValid: false and address: null for non-addresses - Detect duplicates case-insensitively using a normalised lowercase Set; mark only second and subsequent occurrences as isDuplicate: true - Return ParsedRecipient[] — consumed by RecipientInput for live UI feedback and by the validRecipients derivation for the final batchIssueCredential call | - OrganizerIssuePage (sole consumer) - viem isAddress (validation) - parseRecipients.test.ts (verifies verbatim copy) |

| CredentialCard · Component (Student) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Display a student's credential: name, token ID badge, category badge, description (line-clamp-2), activity date, duration, issuer name - Render skill tags as colour-coded badges (colour from SKILL_CATEGORY_COLOURS) with weight multipliers - Show CredentialCardSkeleton (content area placeholders) while isMetadataLoading is true - Provide footer actions: Verify link (pre-fills /verify?tokenId=), Block Explorer link (OP Sepolia), IPFS Metadata link via ipfsToHttp() | - HydratedCredential (useStudentCredentials — data source) - SKILL_CATEGORY_COLOURS / CATEGORY_LABELS (@becp/shared) - Card / Badge / Button (ShadCN UI) - ipfsToHttp / CHAIN (@becp/shared) |

| SkillProgressChart · Component (Student) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Render a Recharts BarChart inside a shadcn ChartContainer; ChartConfig maps skill keys to level-colour CSS variables (--color-<skillKey>) - Order bars: priority skills first (with zero-score placeholders from SKILL_POOL_BY_ID for unearned ones); non-priority skills after at 45% fill opacity - Colour each bar via a custom shape prop SVG <rect> reading var(--color-<skillKey>) so bar colour reflects the skill's current level (beginner → expert) - Draw a dashed ReferenceLine at the first skill's nextLevelThreshold to guide the student toward the next tier - Show a custom tooltip (SkillTooltipContent) with level badge, score, pts-to-next-level, progress percent, credential count | - ChartContainer / ChartConfig / ChartTooltip (shadcn ui/chart) - AggregatedSkillScore[] (useStudentCredentials — data source) - SKILL_LEVELS / scoreToLevel (@becp/shared) - SKILL_POOL_BY_ID (@becp/shared — zero-score placeholders) - BarChart / Bar / ReferenceLine / XAxis / YAxis (Recharts) |

| SoftSkillsRadarChart · Component (Student) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Render a Recharts RadarChart showing all 6 soft skills from SKILL_POOL; unearned skills default to a zero-score placeholder via zeroSoftScore() - Normalise all scores against the Expert threshold (700 pts) so the radar scale is consistent across students at any career stage - Always display all 6 soft skill axes regardless of the student's career goal — soft skills are career-agnostic - Show a custom tooltip (SoftSkillTooltipContent) with level badge, score, pts-to-next-level, credential count | - ChartContainer / ChartTooltip (shadcn ui/chart) - AggregatedSkillScore[] (useStudentCredentials — soft skills only) - SKILL_POOL / SKILL_POOL_BY_ID / SKILL_LEVELS (@becp/shared) - RadarChart / Radar / PolarGrid / PolarAngleAxis (Recharts) |

| RecentCredentialsList · Component (Student) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Render up to maxItems (default 5) most recent credentials as a compact list with award icon, name (truncated), token ID monospace, and category badge - Show a 'View all N credentials' ghost button linking to ROUTES.CREDENTIALS when the full list exceeds maxItems - Show RecentCredentialsListSkeleton (3 skeleton rows) when isLoading is true - Show an empty state icon and 'No credentials yet' label when the credential array is empty | - HydratedCredential[] (useStudentCredentials — data source) - CATEGORY_LABELS / ROUTES (@becp/shared) - Badge / Button / Skeleton (ShadCN UI) - DashboardPage (renders inside Recent Credentials card) |