# BECP — XP Release Plan (Updated: Release 5)

Blockchain-based Extracurricular Credentials Platform  ·  TP075129  ·  APU BSc Software Engineering

Project dates: March 2026 – June 2026  ·  Methodology: Extreme Programming (XP)  ·  Developer: Muhammad Qayyum bin Mahamad Yazid

## 1. Project Overview

BECP is a blockchain-based credential platform issuing soulbound ERC-1155 NFT micro-credentials to university students upon completing extracurricular activities. The system serves four roles — students, organizers, university administrators, and HR recruiters — deployed on Optimism L2. Release 5 migrates both off-chain data stores from local JSON files to Neon Serverless Postgres via Drizzle ORM, adds image support for credential badge artwork and event banners, delivers the event detail page at /events/[tokenId], introduces profile pages for the organizer and admin roles, and applies UX polish including a stable dashboard greeting, corrected block explorer URL format, an ACTIVE_CHAIN constant for automatic mainnet switching, a right-side Drawer on organizer credential type cards, and a bio section in the portfolio PDF. The frontend test suite grows to 225 passing tests across 15 files.

## 2. Release Summary

| Release | Phase(s) | Deliverable | Target | Status |
| --- | --- | --- | --- | --- |
| R1 | Phase 0+1 | Monorepo scaffold + ERC-1155 soulbound smart contract + 52 passing tests + Hardhat 3 deployment config | Week 1–2 | DONE |
| R2 | Phase 2 | Next.js 16 frontend skeleton — wallet auth, role detection, routing, profile API, verify page, 58 tests | Week 3–4 | DONE |
| R3 | Phase 3A–3D | Credential type registration + batch issuance (organizer) + credential gallery + skill progression dashboard (student) — 115 tests | Week 5–7 | DONE |
| R4 | Phase 3E–3G+H | Recruiter QR share + portfolio PDF + admin portal + events marketplace — 177 tests | Week 8–10 | DONE |
| R5 | Phase 4A–4E | Neon + Drizzle DB migration + credential/event images + event detail page + organizer/admin profiles + UX polish — 225 tests | Week 11–12 | DONE |
| R6 | Phase 5 | OP Mainnet production deployment + end-to-end hardening + final evaluator demo preparation | Week 13–14 | PENDING |

## 3. XP Values Applied in Release 5

| XP Value | How it manifests in Release 5 |
| --- | --- |
| Communication | The database migration was specced at the schema and query level before any route code was written — column names, PK strategy (address text PK), upsert semantics (onConflictDoUpdate), and the HTTP driver choice all agreed on paper first. Image upload API contract (allowed MIME types, size limit, returned URI format) documented before form integration began. |
| Simplicity | Drizzle chosen over Prisma because it requires no separate runtime daemon and no migration-file directory — schema.ts is the complete ground truth and drizzle-kit push deploys it in one command. The image upload route reuses the existing Pinata SDK config without a new abstraction layer. Organizer and admin profile pages reuse useStudentProfile and ProfileEditForm with no new hook needed. |
| Feedback | 48 new tests (2 new files, 1 rewrite, 4 additions) give immediate feedback on the Drizzle-backed API routes and EventCard rendering. The Vaul Drawer jsdom mock pattern, the Drizzle queryChunks inspection approach, and the viem isAddress() EIP-55 constraint were all discovered through test failures and documented in CLAUDE.md. |
| Courage | Chose a real Postgres database (Neon) over continuing with JSON files despite the additional environment variable setup. Ruled out Supabase after finding its free-tier inactivity pause would break FYP demo sessions where assessors may visit days after the last activity. |
| Respect | All new and modified source files carry the full programmer header convention with accurate first-written and last-modified dates. CLAUDE.md updated with R5 completed status, the new Vaul Drawer mock pattern, Drizzle mock approach, and viem EIP-55 note for future session continuity. |

# BECP — Iteration Plan: Release 5

Phase 4A (Database Migration) + Phase 4B (Credential & Event Images) + Phase 4C (Event Detail Page) + Phase 4D (UX Polish & Profile Pages) + Phase 4E (Test Suite)  ·  Week 11–12

## 1. Iteration Goals

- Replace both JSON file stores with Neon Serverless Postgres via Drizzle ORM — no change to API consumer interfaces

- Add optional certificate badge and event banner image fields to CredentialTypeMetadata, with upload to IPFS via a new server-side /api/upload-image route

- Deliver the event detail page at /events/[tokenId] showing full credential type information, skills, and an earned/attend CTA

- Add profile pages for organizer and admin roles reusing the existing useStudentProfile hook and ProfileEditForm component

- Apply UX polish: stable dashboard greeting, correct ERC-1155 block explorer URLs, ACTIVE_CHAIN constant, credential-type-card Drawer, bio section in portfolio PDF

- 48 new tests — 2 new test files, 1 full rewrite, 4 additions — growing the suite to 225 across 15 files

## 2. Phase 4A — Centralized Database (Neon + Drizzle ORM)

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Add @neondatabase/serverless and drizzle-orm dependencies; add drizzle-kit as a dev dependency; create drizzle.config.ts pointing at DATABASE_URL. Selection rationale: Neon chosen over Supabase because its free tier has no inactivity pause — a critical requirement for FYP demo sessions where assessors may visit days after the last activity | Qayyum | 0.5 | 0.5 | DONE |
| Write frontend/lib/db/schema.ts — two pgTable definitions: profiles (address text PK, displayName, bio, careerGoal, avatarUri, createdAt, updatedAt) and organizer_requests (address text PK, displayName, organization, reason, status, requestedAt, updatedAt) | Qayyum | 0.5 | 0.5 | DONE |
| Write frontend/lib/db/index.ts — instantiate Neon HTTP driver via neon(DATABASE_URL) and export a Drizzle client via drizzle(sql, { schema }); HTTP driver chosen over TCP to avoid connection pooling issues in Next.js serverless API routes | Qayyum | 0.5 | 0.5 | DONE |
| Rewrite /api/profile/[address] GET and PUT with Drizzle query chains: GET uses db.select().from(profiles).where(eq(profiles.address, addr)); PUT uses db.insert().values(...).onConflictDoUpdate({ target: profiles.address, set: {...} }).returning() — single query handles both first creation and subsequent updates | Qayyum | 1 | 1 | DONE |
| Rewrite /api/organizer-request GET, POST, and PATCH /[address] with Drizzle; GET uses orderBy(asc(organizerRequests.requestedAt)); POST checks for existing non-revoked entry and returns 409 Conflict on duplicate; PATCH uses db.update().set().where(eq(...)).returning() | Qayyum | 1 | 1.5 | DONE |
| Deploy schema to Neon via drizzle-kit push; verify both tables created with correct column types, primary key constraints, and timezone-aware timestamps | Qayyum | 0.5 | 0.5 | DONE |

Phase 4A Total — Estimated: 4 hrs  ·  Actual: 4.5 hrs

## 3. Phase 4B — Credential and Event Images

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Implement /api/upload-image POST route — accepts multipart/form-data with a single "file" field; validates MIME type (image/jpeg, image/png, image/webp only — rejects others with 400) and file size (≤ 2 MB — rejects oversized files with 400); pins accepted files to Pinata via the existing SDK client; returns { uri: "ipfs://..." }; Pinata JWT stays server-side | Qayyum | 1 | 1 | DONE |
| Extend CredentialTypeMetadata interface in lib/credential/metadata.ts with two optional fields: becp_certificate_image (IPFS URI for badge/certificate artwork; also mirrors the ERC-1155 standard image field so wallets display the badge) and becp_event_image (IPFS URI for event banner shown on marketplace cards and the detail page) | Qayyum | 0.5 | 0.5 | DONE |
| Update credential-type-form.tsx to include two image upload inputs (certificate image, event image); each input calls POST /api/upload-image on file selection and stores the returned IPFS URI in form state; shows a preview of the uploaded image | Qayyum | 1.5 | 2 | DONE |
| Update buildCredentialTypeMetadata() to map certificateImageUri to both the standard image field and becp_certificate_image; map eventImageUri to becp_event_image | Qayyum | 0.5 | 0.5 | DONE |
| Update credential-card.tsx to render becp_certificate_image as a card cover image when present (via ipfsToHttp() gateway), falling back to the Award icon | Qayyum | 0.5 | 0.5 | DONE |
| Update event-card.tsx to render becp_event_image as an event banner when present (via ipfsToHttp()), falling back to a placeholder | Qayyum | 0.5 | 0.5 | DONE |

Phase 4B Total — Estimated: 4.5 hrs  ·  Actual: 5 hrs

## 4. Phase 4C — Event Detail Page

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Build frontend/components/ui/breadcrumb-label-context.tsx — React context with leafLabel string and setLeafLabel setter; lets any page push its friendly name into the dashboard header breadcrumb trail without prop-drilling through the layout | Qayyum | 0.5 | 0.5 | DONE |
| Build /events/[tokenId]/page.tsx — reads tokenId from route params and finds the matching MarketplaceEvent in useAllCredentialTypes output; renders: name, organizer/issuer info, category badge, activity date, duration, full description, skills section with SKILL_LEVELS colour dots and weight values, issued count, nftExplorerUrl block explorer link, IPFS metadata link; uses useBreadcrumbLabel to inject credential type name into breadcrumb | Qayyum | 1.5 | 2 | DONE |
| Show "Already Earned" badge when connected student holds this credential (isEarned from useAllCredentialTypes); show a "Browse events" back CTA when not earned | Qayyum | 0.5 | 0.5 | DONE |
| Update event-card.tsx to navigate to /events/[tokenId] on card click using Next.js router; maintain keyboard accessibility with Enter handler | Qayyum | 0.5 | 0.5 | DONE |

Phase 4C Total — Estimated: 3 hrs  ·  Actual: 3.5 hrs

## 5. Phase 4D — UX Polish & Profile Pages

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Fix student dashboard random greeting re-generating on every re-render: replace direct randomGreeting(displayName) call in render with useState(() => randomGreeting(displayName)) lazy initialiser — function runs once on mount, result stored in state and never recomputed | Qayyum | 0.5 | 0.5 | DONE |
| Add ACTIVE_CHAIN constant to shared/constants/index.ts — resolves to CHAIN.OP_SEPOLIA when NODE_ENV !== "production" and CHAIN.OPTIMISM in production; single switch point for the entire application at mainnet deploy time | Qayyum | 0.5 | 0.5 | DONE |
| Add nftExplorerUrl(tokenId) and addressExplorerUrl(address) helpers to shared/contract/addresses.ts — build correct ERC-1155 block explorer URLs using ACTIVE_CHAIN.blockExplorer; nftExplorerUrl produces /nft/{contractAddress}/{tokenId} (correct format for ERC-1155 tokens, not /token/{id}) | Qayyum | 0.5 | 0.5 | DONE |
| Replace all hardcoded block explorer URL constructions across credential-card.tsx, admin pages, and organizer pages with calls to nftExplorerUrl() and addressExplorerUrl() | Qayyum | 1 | 1 | DONE |
| Add Drawer to organizer credential-type-card.tsx — clicking a card opens a right-side Drawer showing full event details; preserves the list-view context so the organizer does not lose their place | Qayyum | 1 | 1.5 | DONE |
| Build /organizer/profile and /admin/profile pages — display name edit form for organizer and admin roles reusing useStudentProfile hook with TanStack Form; read-only wallet address display; add Profile navigation entries to both sidebars | Qayyum | 1 | 1 | DONE |
| Add optional bio Summary section to portfolio-pdf.tsx — when the student has a bio in their profile, render a Summary paragraph below the header; pass bio as a prop from the CredentialsPage through PDFDownloadLink | Qayyum | 0.5 | 0.5 | DONE |

Phase 4D Total — Estimated: 5 hrs  ·  Actual: 5.5 hrs

## 6. Phase 4E — Frontend Test Suite

| Task | Owner | Est (hrs) | Actual (hrs) | Status |
| --- | --- | --- | --- | --- |
| Rewrite tests/unit/api-profile.test.ts for Drizzle mock — replace fs/promises mock with an in-memory Map-backed db mock; implement extractAddress() helper that inspects Drizzle eq() queryChunks (SQL AST objects) to extract bound address values; 10 tests covering GET 200/404, PUT upsert, invalid address 400, address normalisation to lowercase | Qayyum | 1 | 1.5 | DONE |
| Write tests/unit/api-organizer-request.test.ts — 25 tests covering GET list, POST submit (valid request, invalid address 400, duplicate rejection 409, address normalisation), PATCH status update (found, not found); same Drizzle mock pattern with module-level _pendingSet variable to capture .set() values across the chained .set().where().returning() call | Qayyum | 1.5 | 2 | DONE |
| Write tests/components/EventCard.test.tsx — 19 tests covering skeleton rendering, full card with metadata, Already Earned badge when isEarned is true, skill tag display with category colours, card click navigation to /events/[tokenId], image rendering when becp_event_image is present | Qayyum | 1 | 1.5 | DONE |
| Add 4 Drawer tests to tests/components/CredentialCard.test.tsx (20 total) — mock Vaul Drawer with a React Context-based controlled implementation using vi.mock async factory (async () => { const { ... } = await import("react") }) to avoid module-hoisting scope errors; test Drawer opens on card click and renders full detail content | Qayyum | 1 | 1.5 | DONE |

Phase 4E Total — Estimated: 4.5 hrs  ·  Actual: 6.5 hrs

Release 5 Total — Estimated: 21 hrs  ·  Actual: 25 hrs

## 7. Retrospective Notes

| Category | Note |
| --- | --- |
| Went well | Neon Serverless Postgres with the HTTP driver was the right fit for Next.js API routes. No connection pooling issues, no separate server process, and drizzle-kit push deployed the schema in a single command. The onConflictDoUpdate pattern cleanly replaces the read-then-write JSON file logic with a single atomic query. |
| Went well | Organizer and admin profile pages required zero new hooks or API changes — useStudentProfile and ProfileEditForm composed without modification. Reuse of existing infrastructure is the correct XP simplicity call. |
| Went well | The ACTIVE_CHAIN constant and the two explorer URL helpers cleanly resolved the dual-network problem. Every block explorer URL in the application now flows through two functions, eliminating hardcoded chain references and making the mainnet switch a one-variable change. |
| Went over | The Drizzle mock for unit tests required more design than estimated. Drizzle eq() produces a SQL AST object rather than a plain value, so tests cannot inspect the condition argument directly — they must traverse queryChunks to extract the bound parameter. The update chain (.set().where().returning()) required a module-level _pendingSet variable to bridge the two chained calls because .set() and .returning() execute at different points in the chain. |
| Went over | Mocking Vaul Drawer in jsdom was the most complex test problem in the release. Vaul uses Web Animations API and requestAnimationFrame, both absent in jsdom. A React Context-based controlled mock was required. Using vi.mock with an async factory (async () => { const { ... } = await import("react") }) was necessary to avoid the hoisting-scope restriction that prevents outer-scope variables from being referenced in mock factories. |
| Learned | viem isAddress() validates EIP-55 checksum for mixed-case addresses. An all-uppercase hex string (e.g. produced by String.toUpperCase()) does not pass checksum and returns false. Tests asserting address normalisation must use a properly checksummed address as input — not an artificially capitalised string. |
| Learned | vi.mock factory functions are hoisted above all imports and cannot reference any outer-scope variables. Async factories using await import() inside the factory are the correct pattern when dependencies need to be imported within a mock factory. |
| Action item | For R6: OP Mainnet production deployment. ACTIVE_CHAIN, nftExplorerUrl, and addressExplorerUrl are already in place; the remaining work is deploying the contract to Optimism mainnet, setting NEXT_PUBLIC_CONTRACT_ADDRESS, and setting DATABASE_URL in the production environment. |
| Action item | For R6: prepare the evaluator demo script — a walkthrough of the full credential lifecycle (register type → batch issue → student views gallery → skill dashboard → QR share → recruiter verify → admin portal → PDF export) on OP Mainnet. |

# BECP — User Stories: Release 5

Phase 4A–4D  ·  US-24 through US-28  ·  All stories verified by passing test suite

## US-24 — Developer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-24 | Developer (Qayyum) | Must Have | R5 / Phase 4A | DONE |

"As the developer, I want to replace both JSON file stores with a real database so that the platform is stable for the FYP evaluator demo environment and not at risk from file I/O concurrency or server restart data loss."

Acceptance Criteria:

- ✓ Both /api/profile/[address] and /api/organizer-request routes use Neon Serverless Postgres via Drizzle ORM — no fs module dependencies remain in either route

- ✓ The profiles table stores address (PK), displayName, bio, careerGoal, avatarUri, and timezone-aware timestamps

- ✓ The organizer_requests table stores address (PK), displayName, organization, reason, status, and timezone-aware timestamps

- ✓ PUT /api/profile uses onConflictDoUpdate — a single atomic query handles both first creation and subsequent updates

- ✓ POST /api/organizer-request returns 409 Conflict when a non-revoked request for the same address already exists

- ✓ All existing API consumers (useStudentProfile, useOrganizerRequests, admin pages) work without interface changes

- ✓ Schema is deployed to Neon via drizzle-kit push; DATABASE_URL is read from environment variables

Test coverage: api-profile.test.ts (rewritten, 10 tests) + api-organizer-request.test.ts (new, 25 tests)

## US-25 — Organizer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-25 | Organizer | Must Have | R5 / Phase 4B | DONE |

"As an organizer, I want to upload a certificate badge image and an event banner image when registering a credential type so that credential cards and marketplace listings look polished and recognisable."

Acceptance Criteria:

- ✓ The credential type registration form includes two optional image upload inputs: certificate/badge image and event banner image

- ✓ Selecting a file calls POST /api/upload-image; only JPEG, PNG, and WebP files ≤ 2 MB are accepted; invalid MIME type or oversized files return an error

- ✓ After a successful upload a preview of the image is shown in the form and the resulting ipfs:// URI is stored in form state

- ✓ buildCredentialTypeMetadata() maps the certificate image URI to the standard ERC-1155 image field (so wallets display it) and to becp_certificate_image; maps the event image to becp_event_image

- ✓ CredentialCard renders becp_certificate_image as a card cover (via ipfsToHttp()) when present; falls back to the Award icon when absent

- ✓ EventCard renders becp_event_image as a banner when present; falls back to a placeholder when absent

- ✓ The Pinata JWT is never exposed to the browser — the upload is routed through the server-side /api/upload-image handler

Test coverage: EventCard.test.tsx — image rendering when becp_event_image is present

## US-26 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-26 | Student | Must Have | R5 / Phase 4C | DONE |

"As a student, I want to view the full details of an event before deciding to attend so that I understand what skills I will earn, who the organizer is, and how many peers have already participated."

Acceptance Criteria:

- ✓ Clicking an event card on the marketplace navigates to /events/[tokenId]

- ✓ The detail page shows: credential type name, organizer/issuer info, activity category badge, activity date, duration, full description, skills section with level colour dots and weight values, issued count

- ✓ Links to the block explorer (using nftExplorerUrl) and IPFS metadata are shown

- ✓ If the connected student already holds this credential, an "Already Earned" badge is shown

- ✓ The breadcrumb trail in the dashboard header shows the credential type name via BreadcrumbLabelContext

- ✓ Loading skeletons are shown while data is loading; a not-found empty state is shown for an unknown tokenId

Test coverage: Manual — page rendering verified by inspection; hook coverage from useAllCredentialTypes.test.ts (R4) carries forward

## US-27 — Student

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-27 | Student | Should Have | R5 / Phase 4D | DONE |

"As a student, I want the dashboard greeting to stay consistent throughout my session so that the message does not change unexpectedly when the page re-renders."

Acceptance Criteria:

- ✓ The greeting (e.g. "Welcome, Qayyum!" or "Ready to level up, Qayyum?") is chosen once on component mount and remains stable for the entire session

- ✓ Implementation uses useState(() => randomGreeting(displayName)) lazy initialiser — the function is called exactly once, not on every render

- ✓ Subsequent re-renders caused by credential data loading or profile updates do not change the greeting

Test coverage: Manual — verified by inspection; no dedicated automated test

## US-28 — Developer

| Story ID | Role | Priority | Iteration | Status |
| --- | --- | --- | --- | --- |
| US-28 | Developer (Qayyum) | Should Have | R5 / Phase 4D | DONE |

"As the developer, I want all block explorer links to use the correct ERC-1155 URL format and to automatically point to the correct network in production so that links work without code changes at mainnet deploy time."

Acceptance Criteria:

- ✓ nftExplorerUrl(tokenId) produces {blockExplorer}/nft/{contractAddress}/{tokenId} — the correct ERC-1155 token path (replaces the incorrect /token/{id} format used in earlier releases)

- ✓ addressExplorerUrl(address) produces {blockExplorer}/address/{address}

- ✓ Both helpers are exported from shared/contract/addresses.ts and use ACTIVE_CHAIN so no change is needed at mainnet deploy

- ✓ ACTIVE_CHAIN in shared/constants/index.ts resolves to CHAIN.OP_SEPOLIA in development (NODE_ENV !== "production") and CHAIN.OPTIMISM in production

- ✓ All components that previously hardcoded block explorer URL construction now call the helper functions

Test coverage: Manual — verified by inspection of generated links in development environment

# BECP — CRC Cards: Release 5 Frontend & Shared Layer

Component Responsibility Collaborator cards for the Phase 4A–4D additions

| lib/db/schema.ts + lib/db/index.ts · Database Layer |  |
| --- | --- |
| Responsibilities | Collaborators |
| - schema.ts: define two Drizzle pgTable schemas — profiles (address text PK, displayName, bio, careerGoal, avatarUri, timezone-aware timestamps) and organizer_requests (address text PK, displayName, organization, reason, status, timezone-aware timestamps) - index.ts: instantiate Neon HTTP driver with neon(process.env.DATABASE_URL) and export the Drizzle client as db via drizzle(sql, { schema }) - Provide the single db export consumed by all three API routes — no route imports Neon or Drizzle directly - Schema deployed via drizzle-kit push; drizzle.config.ts reads DATABASE_URL and points at the frontend/lib/db directory | - @neondatabase/serverless neon() (HTTP driver) - drizzle-orm/neon-http drizzle() (ORM client) - /api/profile/[address] (consumer) - /api/organizer-request and /api/organizer-request/[address] (consumers) |

| /api/upload-image · API Route (Image Upload to IPFS) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Accept a multipart/form-data POST with a single "file" field - Validate MIME type — accept image/jpeg, image/png, image/webp; reject all others with 400 Bad Request - Validate file size — reject files over 2 MB with 400 Bad Request - Pin accepted files to Pinata using the existing lib/pinata/config.ts SDK client; return { uri: "ipfs://..." } - Keep Pinata JWT server-side at all times — the route is the only code path that touches the key | - lib/pinata/config.ts (Pinata SDK client) - credential-type-form.tsx (upload call site on file select) - NextRequest FormData / File API (request parsing) |

| CredentialTypeMetadata — becp_certificate_image / becp_event_image · Metadata Extension |  |
| --- | --- |
| Responsibilities | Collaborators |
| - becp_certificate_image (optional string): IPFS URI for the badge/certificate artwork; also mirrors the standard ERC-1155 image field so blockchain wallets display the badge image correctly - becp_event_image (optional string): IPFS URI for the event banner displayed on marketplace event cards and the event detail page - Both fields are optional — credential types created before R5 continue to function with icon fallbacks - buildCredentialTypeMetadata() maps certificateImageUri to both image and becp_certificate_image; maps eventImageUri to becp_event_image | - lib/credential/metadata.ts (interface definition + buildCredentialTypeMetadata) - credential-type-form.tsx (upload and form state) - /api/upload-image (upload target) - credential-card.tsx, event-card.tsx, events/[tokenId]/page.tsx (render consumers) |

| events/[tokenId]/page.tsx · Page (Event Detail) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Read tokenId from Next.js route params; find the matching MarketplaceEvent in useAllCredentialTypes output - Render full credential type detail: name, organizer/issuer name and address, category badge, activity date, duration, full description, skills section with SKILL_LEVELS colour indicators and weight values, issued count - Show nftExplorerUrl(tokenId) block explorer link and ipfsToHttp(metadataURI) IPFS metadata link - Show "Already Earned" badge when isEarned is true for the connected wallet; show a "Browse events" CTA when not earned - Push the credential type name into BreadcrumbLabelContext so the dashboard header breadcrumb shows a friendly name instead of the raw tokenId path segment - Show loading skeletons while data is fetching; show not-found empty state when tokenId is absent from active types | - useAllCredentialTypes (MarketplaceEvent data source) - useBreadcrumbLabel (breadcrumb label injection) - nftExplorerUrl / ipfsToHttp / SKILL_LEVELS / CATEGORY_LABELS (@becp/shared) - Card / Badge / Skeleton / Empty (ShadCN UI) - events/page.tsx (navigates here on card click) |

| BreadcrumbLabelContext · Context (Dynamic Breadcrumb Labelling) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Provide a React context with leafLabel (string ¦ null) and setLeafLabel setter - Any page component can call useBreadcrumbLabel().setLeafLabel(name) to override the leaf segment of the breadcrumb shown in DashboardHeader - DashboardHeader reads leafLabel and falls back to the path-derived segment label when null - Eliminates the need to prop-drill dynamic names through the layout hierarchy for detail pages | - frontend/components/ui/breadcrumb-label-context.tsx (context definition) - events/[tokenId]/page.tsx (writes credential type name) - DashboardHeader component (reads and renders label) |

| ACTIVE_CHAIN / nftExplorerUrl / addressExplorerUrl · Shared Constants & Helpers |  |
| --- | --- |
| Responsibilities | Collaborators |
| - ACTIVE_CHAIN (shared/constants/index.ts): resolves to CHAIN.OP_SEPOLIA when NODE_ENV !== "production", CHAIN.OPTIMISM in production — the single switch point for the entire application at mainnet deploy time - nftExplorerUrl(tokenId) (shared/contract/addresses.ts): builds {ACTIVE_CHAIN.blockExplorer}/nft/{contractAddress}/{tokenId} using the correct ERC-1155 token URL format - addressExplorerUrl(address) (shared/contract/addresses.ts): builds {ACTIVE_CHAIN.blockExplorer}/address/{address} - Both helpers call getContractAddress(ACTIVE_CHAIN.id) internally so the correct deployed contract address is always used without requiring it to be passed as an argument | - shared/constants/index.ts (ACTIVE_CHAIN) - shared/contract/addresses.ts (helper definitions) - credential-card.tsx, events/[tokenId]/page.tsx, admin pages, organizer pages (consumers) |

| organizer/profile + admin/profile · Pages (Role Profile) |  |
| --- | --- |
| Responsibilities | Collaborators |
| - Render a display name edit form for the organizer and university admin roles — each page uses the existing useStudentProfile hook for data fetching and mutation, and TanStack Form for field management; no new hook, API route, or database column required - Show a read-only wallet address field (identical to the student profile page pattern) - Save button enabled only when the form is dirty; shows an "Up to date" indicator when clean - Add "Profile" navigation entries to the organizer sidebar and the admin sidebar | - useStudentProfile (profile data + saveProfile mutation) - TanStack Form useForm (field management) - organizer-sidebar.tsx, admin-sidebar.tsx (navigation entries added) - PageHeader / Card / Field / Input / Button (ShadCN UI) |